## MC Annual Plan
| Issue Title | Strategic Focus Area | Issue Status | Date Created | Target Completion | FERC Filing | <= 2013 | 2014 Jan | 2014 Feb | 2014 Mar | 2014 Apr | 2014 May | 2014 Jun | 2014 Jul | 2014 Aug | 2014 Sep | 2014 Oct | 2014 Nov | 2014 Dec | >= 2015
MRC | Interregional Coordination | Reliability/Markets | Solution Alternatives Proposed | 2008-06-11 | 2014-12-31 | TBD
OC | Combined Cycle Modeling | Competitive Markets | On Hold | 2012-03-26 | 2015-12-31 | No
MRC | CT Lost Opportunity Cost | Competitive Markets | Cancelled | 2012-10-10 | 2012-12-20 | TBD
MRC | PJM/NYISO Coordinated Transaction Schedules (CTS) | Competitive Markets | Awaiting Sr. Committee Approval | 2012-12-20 | 2014-06-01 | Yes
MIC | DR Existing MW Proposed Manual Change | Competitive Markets | Complete | 2013-03-28 | 2014-05-29 | TBD
MIC | Replacement Capacity | Competitive Markets | Complete | 2013-03-06 | 2014-02-27 | TBD
MRC | Gas/Electric Coordination: Timing of PJM's Day-Ahead Market | Reliability/ Operations | On Hold | 2013-03-28 | 2014-09-30 | TBD
MRC | Gas/Electric Coordination: Fuel Firming Generator Availability | Reliability/ Operations | On Hold | 2013-03-28 | 2014-09-30 | TBD
MRC | PJM/MISO JCM Initiatives | Competitive Markets | Evaluation in Progress | 2013-03-28 | 2015-07-06 | TBD
MIC | Energy Schedules | Competitive Markets | On Hold | 2013-04-10 | 2014-09-30 | TBD
MIC | Frequently Mitigated Units | Competitive Markets | Complete | 2013-04-10 | 2014-07-01 | TBD
MRC | System Restoration Strategy | Reliability/Operations | Awaiting Sr. Committee Approval | 2013-04-25 | 2013-12-31 | Yes
MRC | Energy Market Uplift (Cold Weather Report Recommendation) | Reliability/Markets/Ops | Solution Alternatives Proposed | 2013-05-30 | 2014-12-31 | TBD
MRC | MOPR Unit-Specific Exemption | Reliability/Markets | Awaiting Sr. Committee Approval | 2013-05-30 | 2014-04-24 | Yes
MIC | Published RPM Supply Curve Transparency | Competitive Markets | Awaiting Sr. Committee Approval | 2013-06-05 | 2014-03-27 | TBD
MRC | RPM – Non-firm Capacity Resource Incentives | Competitive Markets | Complete | 2013-08-01 | 2014-02-27 | Yes
PC | Performance of Generator Seasonal Verification Tests | Reliability/Operations | Complete | 2013-08-08 | 2014-02-27 | Yes
MRC | CONE Triennial Review Process | Competitive Markets | Complete | 2013-08-29 | 2014-03-31 | Yes
MIC | Energy & Reserves Pricing and Interchange Volatility (Cold Weather Report Recommendation) | Reliability/Operations | Evaluation in Progress | 2013-11-21 | 2014-06-01 | TBD
MRC | Emergency Annual Demand Response Maintenance Outage Reporting Process | Reliability/Operations | Solution Alternatives Proposed | 2013-12-12 | 2014-06-01 | TBD
MIC | Financial & Node Limitation on Up-to Congestion Transactions | Competitive Markets | Solution Alternatives Proposed | 2013-12-12 | 2014-10-01 | Yes
MRC | Gas/Electric Coordination: Communication | Reliability/Operations | Complete | 2014-01-30 | 2014-02-27 | Yes
MIC | QTU Deficiency Charge and Credit Rate | Competitive Markets | Solution Alternatives Proposed | 2014-01-30 | 2014-09-30 | Yes
PC | Small Generator Interconnection Procedures/Agreements | Reliability/Operations | Evaluation in Progress | 2014-02-06 | 2014-08-03 | Yes
MIC | Residential DR Participating in the PJM SR Market | Competitive Markets | Solution Alternatives Proposed | 2014-02-07 | 2014-09-30 | Yes
MRC | Enhanced Inverter Capabilities | Reliability/Operations | Solution Alternatives Proposed | 2014-02-27 | 2014-08-01 | TBD
MIC | Offer Cap Review (Cold Weather Report Recommendation) | Competitive Markets | Solution Alternatives Proposed | 2014-03-27 | 2014-08-31 | TBD
OC | TO Data Feed (Generator Data Confidentiality Process) | Reliability/Operations | Interest Identifiation | 2014-03-27 | 2014-08-31 | TBD
MRC | FTR Forfeiture Rule Review | Competitive Markets | On Hold | 2013-05-30 | 2014-08-01 | Yes
PC | Energy Storage Resources | Reliability/Operations | Solution Alternatives Proposed | 2013-08-29 | 2014-08-30 | Yes
MRC | Auction Specific Transactions in RPM | Competitive Markets | Awaiting Sr. Committee Approval | 2014-04-24 | 2014-09-30 | TBD
MIC | DR Emergency Energy Settlement M&V | Competitive Markets | Evaluation in Progress | 2014-05-07 | 2014-10-31 | TBD
OC | Cold Weather Resource Improvement/ Winter Testing Requirements (Cold Weather Report Recommendation) | Reliability/Operations | Interest Identifiation | 2014-05-06 | 2014-10-01 | Yes
MRC | FTR Market Enhancements | Competitive Markets | Education in Progress | 2014-05-29 | 2014-10-30 | Yes
OC | Gas-Fired Unit Commitment Coordination (Cold Weather Report Recommendation) | Reliability/ Operations | Evaluation in Progress | 2014-05-29 | 2014-10-30 | TBD
MIC | M&V for Residential DR in Energy & Capacity Markets | Competitive Markets | Evaluation in Progress | 2014-04-09 | 2014-12-31 | TBD
MRC | RPM Triennial Review | Competitive Markets | Evaluation in Progress | 2014-04-15 | 2014-08-31 | TBD
RPPTF | Multi-Driver Approach and Associated Issues | Reliability/Operations | Awaiting Sr. Committee Approval | 2011-02-01 | 2014-10-31 | Yes
MRC | Generation Capacity Resource Performance (Cold Weather Report Recommendation) | Reliability/Operations | Problem Statement Initiated | 2014-06-26 | 2014-11-20 | Yes
MIC | Unit Market Offers (Cold Weather Report Recommendation) | Competitive Markets | Problem Statement Not Initiated | 2014-07-09 | 2014-11-20 | TBD
MIC | Regulation Market Rules (Cold Weather Report Recommendation) | Competitive Markets | Problem Statement Not Initiated | 2014-07-09 | 2014-11-20 | TBD
MC | Withdrawal Timing Requirements | Governance | Solution Alternatives Proposed | 2013-11-16 | 2014-09-30 | Yes
Highest Priority
Virtually done
Being worked in standard committee meetings
Candidates for deferral
JCM