## Sheet1
Region | Upgrade ID | Description | Transmission Owner | Required In Service Date | Revised Required In Service Date | Status | TEAC Cost | TEAC Date | Latest TEAC Date | Notes | Board Date | Initial Issue Assessment | Final Assessment
PJM WEST | b3717.3 | Relay work at Springdale 138 kV. | DL | 2024-12-31 |  | PL | 1 | 2023-05-09 |  |  |  | Scope/Cost Change | Scope/Cost Change
PJM WEST | b3717.4 | Transmission Line work – a new transmission structure and necessary tower work to handle the change in tension at Cheswick 138 kV. | DL | 2025-01-01 |  | PL | 2 | 2023-05-09 |  |  |  | Scope/Cost Change | Scope/Cost Change
PJM MA | b3737.22 | Construct the Larrabee Collector station AC switchyard, composed of a 230 kV 3 x breaker and a half substation with a nominal current rating of 4000 A and four single phase 500/230 kV 450 MVA autotransformers to step up the voltage for connection to the Smithburg substation. Procure land adjacent to the AC switchyard, and prepare the site for construction of future AC to DC converters for future interconnection of DC circuits from offshore wind generation. Land should be suitable to accommodate installation of four individual converters to accommodate circuits with equivalent rating of 1400 MVA at 400 kV. | MAOD | 2027-12-31 |  | PL | 193.3 | 2022-11-04 | 2023-05-09 | 2021_SAA-550 | 2022-12-06 | Scope/Cost Change | Scope/Cost Change
PJM MA | b3737.27 | Rebuild approximately 0.8 miles of the D1018 (Clarksville-Lawrence 230 kV) line between Lawrence substation (PSEG) and structure No. 63. | JCPL | 2029-06-01 |  | EP | 14.58 | 2022-11-04 | 2023-05-09 | 2021_SAA-17 | 2022-12-06 | Scope/Cost Change | Scope/Cost Change
PJM MA | b3737.33 | Reconductor Red Oak A-Raritan River 230 kV. | JCPL | 2029-06-01 |  | EP | 12.53 | 2022-11-04 | 2023-05-09 |  | 2022-12-06 | Scope/Cost Change | Scope/Cost Change
PJM MA | b3737.35 | Reconductor small section of Raritan River-Kilmer I 230 kV. | JCPL | 2029-06-01 |  | EP | 27.3 | 2022-11-04 | 2023-05-09 |  | 2022-12-06 | Scope/Cost Change | Scope/Cost Change
PJM MA | b3737.38 | Linden subproject: Install a new 345/230 kV transformer at the Linden 345 kV Switching station, and relocate the Linden-Tosco 230 kV (B-2254) line from the Linden 230 kV to the existing 345/230 kV transformer at Linden 345 kV. | PSEG | 2027-12-31 |  | PL | 35.3 | 2022-11-04 | 2023-05-09 | 2021_SAA-180 | 2022-12-06 | Scope/Cost Change | Scope/Cost Change
PJM MA | b3737.40 | Windsor to Clarksville subproject: Reconductor one span of the C1017 (Clarksville-Windsor) 230kV line from structure #126 to Windsor Substation with double bundled 1590 ACSR conductor, approximately (0.1) mile. | JCPL | 2029-06-01 |  | EP | 1.72 | 2022-11-04 | 2023-05-09 | 2021_SAA-180 | 2022-12-06 | Scope/Cost Change | Scope/Cost Change
PJM MA | b3737.42 | Upgrade inside plant equipment at Lake Nelson I 230 kV. | PSEG | 2029-06-01 |  | PL | 4.8 | 2022-11-04 | 2023-05-09 |  | 2022-12-06 | Scope/Cost Change | Scope/Cost Change
PJM MA | b3737.43 | Upgrade Kilmer W-Lake Nelson W 230 kV line drop and strain bus connections at Lake Nelson 230 kV. | PSEG | 2029-06-01 |  | PL | 0.57 | 2022-11-04 | 2023-05-09 |  | 2022-12-06 | Scope/Cost Change | Scope/Cost Change
PJM MA | b3737.44 | Upgrade Lake Nelson-Middlesex-Greenbrook W 230 kV line drop and strain bus connections at Lake Nelson 230 kV. | PSEG | 2029-06-01 |  | PL | 0.58 | 2022-11-04 | 2023-05-09 |  | 2022-12-06 | Scope/Cost Change | Scope/Cost Change
PJM MA | b3737.48 | Build a new North Delta-Graceton 230 kV line by rebuilding 6.26 miles of the existing Cooper-Graceton 230 kV line to double circuit. Cooper-Graceton is jointly owned by PECO & BGE. This subproject is for PECO's portion of the line rebuild which is 4.1 miles. | PECO | 2029-06-01 |  | PL | 18.82 | 2022-11-04 | 2023-05-09 | 2021_SAA-63 | 2022-12-06 | Scope/Cost Change | Scope/Cost Change
PJM MA | b3737.53 | Remove the existing E83 Line 115 kV (not in-service) to accommodate the new 500kV/230kV lines (approximately 7.7 miles). | JCPL | 2027-12-31 |  | PL | 8.47 | 2023-05-09 |  | 2021_SAA-453 |  | Scope/Cost Change | Scope/Cost Change
PJM MA | b3737.54 | Remove the existing H2008 Larrabee-Smithburg No. 2 230 kV to accommodate the new 500kV/230kV lines. | JCPL | 2027-12-31 |  | PL | 8.47 | 2023-05-09 |  | 2021_SAA-453 |  | Scope/Cost Change | Scope/Cost Change
PJM MA | b3737.55 | Middlesex Substation 230kV - Replace the 2000A Circuit Switcher at Middlesex Switch point for the Lake Nelson I1023 230kV exit | JCPL | 2029-06-01 |  | PL | 0.53 | 2023-05-09 |  | 2021_SAA-17 |  | Scope/Cost Change | Scope/Cost Change
PJM MA | b3737.56 | Build a new North Delta-Graceton 230 kV line by rebuilding 6.26 miles of the existing Cooper-Graceton 230 kV line to double circuit. Cooper-Graceton is jointly owned by PECO & BGE. This subproject is for BGE's portion of the line rebuild which is 2.16 miles. | BGE | 2029-06-01 |  | PL | 9.92 | 2023-05-09 |  | 2021_SAA-63 |  | Scope/Cost Change | Scope/Cost Change
PJM MA | b3737.59 | Windsor to Clarksville subproject: Upgrade terminal equipment at Windsor 230 kV. | JCPL | 2029-06-01 |  | PL | 1.58 | 2023-05-09 |  | 2021_SAA-180 |  | Scope/Cost Change | Scope/Cost Change
PJM MA | b3737.60 | Perform a Pre-build Infrastructure evaluation study in alignment with the NJBPU Solicitation Guidance Document requirements. | MAOD | 2023-06-02 |  | PL | 0.29 | 2023-05-09 |  | 2021_SAA-550 |  | Scope/Cost Change | Scope/Cost Change
PJM WEST | b3775.11 | Upgrade the limiting element at Stillwell substation to increase the rating of the Stillwell-Dumont 345 kV line to match conductor rating. | AEP | 2026-12-01 |  | PL | 1.78 | 2023-04-11 |  | 2022_MD-644 (modified) |  | Scope/Cost Change | Scope/Cost Change
PJM WEST | b3775.6 | Perform sag study mitigation work on the Dumont-Stillwell 345 kV line (remove a center-pivot irrigation system from under the line, allowing for the normal and emergency ratings of the line to increase, replace two structures and modify a third structure). | AEP | 2026-12-01 |  | PL | 2.22 | 2023-01-10 | 2023-04-11 | 2022_MD-644 (modified) | 2023-02-15 | Scope/Cost Change | Scope/Cost Change
PJM WEST | b3775.7 | Upgrade the limiting element at Dumont substation to increase the rating of the Stillwell-Dumont 345 kV line to match conductor rating. | AEP | 2026-12-01 |  | PL | 1 | 2023-01-10 | 2023-04-11 | 2022_MD-644 (modified) | 2023-02-15 | Scope/Cost Change | Scope/Cost Change
PJM WEST | b3777 | Disconnect and remove three 345 kV breakers, foundations, and associated equipment from Sammis substation. Remove nine 345 kV CVT’s. Remove two 345 kV disconnect switches. Install new 345 kV buswork and foundations. Install new fencing. Remove and adjust relaying at Sammis substation. | ATSI | 2023-06-01 |  | PL | 2.1 | 2023-05-09 |  |  |  | New Upgrade | New Upgrade
PJM WEST | b3778 | Remove the Pleasants #1 and Pleasants #2 500 kV line exits at Belmont Substation. Remove the Belmont – Pleasants 500 kV #1 and #2 Transmission Lines. Modify relay settings at Belmont Substation. | APS | 2023-06-01 |  | PL | 0.67 | 2023-05-09 |  |  |  | New Upgrade | New Upgrade
PJM SOUTH | b3779 | Cut existing 230kV line #2183 and extend from Poland Road substation to Evergreen Mills substation. Approximately 0.59 miles of new line will be built from the cut-in to the Evergreen Mills substation. Cut and extend the existing 230kV line #2183 creating a new line #2210 from Brambleton substation to be terminated at Evergreen Mills substation. Approximately 0.59 miles of new line will be built from the cut-in to the Evergreen Mills substation. | Dominion | 2027-06-01 |  | PL | 7.71 | 2023-04-11 |  | 2022_2-648 |  | New Upgrade | New Upgrade
PJM MA | b2633.91 | Implement changes to the tap settings for the two Salem units' step up transformers | PSEG Nuclear | 2019-04-01 | 2020-06-01 | EP | 0.01 | 2015-04-28 | 2017-03-03 | 2013_1-5A (AI) | 2015-07-29 | Cancelled in Database | Cancelled
PJM MA | b2633.92 | Implement changes to the tap settings for the Hope Creek unit's step up transformers | PSEG Nuclear | 2019-04-01 | 2020-06-01 | EP | 0.01 | 2015-04-28 | 2017-03-03 | 2013_1-5A (AI) | 2015-07-29 | Cancelled in Database | Cancelled
PJM MA | b3737.51 | Replace four 63 kA circuit breakers "205," "235," "225" and "255" at Peach Bottom 500 kV with 80 kA. | PECO | 2029-06-01 |  | PL | 5.6 | 2022-11-04 |  |  | 2022-12-06 | Cancelled in Database | Cancelled