## Sheet1
| Clean Attribute Procurement Senior Task Force (CAPSTF) - Work Plan | 6/3/22 | 6/28/22 | 7/28/22 | 8/17/22 | 9/13/22 | 10/12/22 | 11/4/22 | 12/16/22 | Jan | Feb | Mar | Apr | May | Jun
Education & Fact Finding | Develop Work Plan (KWA #1) | X | X | X
| Education & Joint Fact-Finding (KWA #1) | X | X | X | X | X | X
| Interest Identification (KWA #2) |  | X | X
Conceptual Design | Develop Representative Market Design Options (KWA #3) |  |  | X | X | X
| Develop Design Components (KWA #3) |  |  |  | X | X
| Document Relative Importance of each Component (KWA #3) |  |  |  |  | X
| Develop Options for each Component (KWA #4) |  |  |  |  | X | X | X
| Narrow Options (KWA #4) | [6 empty] | X
| Determine questions to be explored via analysis (KWA #5) |  | X | X | X | X | X | X
| Determine analytical approach and conduct analysis (KWA #6) |  |  |  | X | X | X | X | X
| Analysis Results Discussion (KWA #6) | [7 empty] | X (initial results) | bar: Jan to Jun
| Develop Packages (KWA #4) | [7 empty] | X | bar: Jan to Jun
Narrow Packages (KWA #7) | bar: Jan to Jun
Consensus Testing (KWA #7) | bar: Jan to Jun
Tier 1/Tier 2 Decision Making (KWA #7) | bar: Jan to Jun
Reporting Conceptual Design to Parent Committee (MRC) (KWA #7) | bar: Jan to Jun
Detailed Design | Develop Manual Language (as necessary) (KWA #8)
Develop Tariff Language (as necessary) (KWA #8)
Tier 1/Tier 2 Decision Making (KWA #8)
Reporting to Parent Committee [MRC (MC if needed)] (KWA #8)
Updated: Oct 26, 2022
Issue Charge