## Interests
PJM Capacity Senior Task Force
Demand Response Issues
Interests
Address short-term Demand Response issues listed in issue charge.
Updated November 19, 2012
ID | Stakeholder Interests and Concerns
1 | Options to improve customers' ability to hedge RPM costs, or avoid them altogether
2 | Determining the makeup of BTM generation as part of the DR mix as a whole
3 | Maintain reliability
4 | Minimize perverse incentives
5 | Minimize administrative barriers to entry and administrative costs
6 | Comparably situated customers should have comparable ability to participate in DR
7 | DR should be treated comparably, but not necessarily identically, to generation
8 | DR and Generation should be treated comparably in terms of their obligations as RPM resources
9 | DR should be treated comparably to PRD
10 | Maintaining a process to manage and offset base load
11
12

## Design Components
PJM Capacity Senior Task Force
Demand Response Issues
Design Components
Address short-term Demand Response issues listed in issue charge.
Updated January 22, 2013
ID | Design Component/Issue | Importance | Component Options
|  |  | Status Quo | A | B | C | D | E | F | G
1 | Auditing of DR contracts | 6 | If DR does not perform they receive a penalty. CSP permitted to aggregated performance across customers. MMU, PJM and FERC OE may investigate on case by case basis as necessary | ** See tab titled "Audit Design Components" for investigation around this item.
2 | DR test may not be adequate for DR Products. DR offers into market but may not have the capability to perform based on product requirements (Limited, Extended Summer and/or Annual) | 2 | CSP is required to simultaneously test all their DR resources in a zone for 1 hour (determined by CSP) if PJM has not called an event in that zone by August 15 (see slides from 9/20/2012 meeting) | Require additional tests during non-summer period for Extended Summer and Annual products. | Allow for random tests of all product types by PJM but tests are product type specific.
3a | Customer Peak Load Contribution (PLC) Risk - Customer wants to be fully interruptible but does not know PLC 3 years in advance for Base Residual Auction (BRA) | 1 | DR resources are managed as portfolio by CSP in wholesale market. CSP may adjust portfolio of customers after customer PLCs are establish to meet commitments. | Provide for the allocation of excess commitment credits to registered DR customers | Existing/pre-registered DR resources can offer a curtailment up to its non-coincident peak demand.
3b | PLC accuracy - Current EDC customer PLC allocation methodology may not be adequate. | 1 | EDC determines PLC customer allocation process and in most situations uses 5CP approach as basis
3c | PLC accuracy - Customer load changes (growth or decline) are not incorporated in PLC until ~1 year later. | 1 | PLC calculated based on prior summer load. If customer load will go up before PLC goes up then will receive lower capacity allocation. If customer load will go down before PLC goes down then may nominate additional amount as DR.
5 | Measurement and Verification of recently added products: some load may be nominated as Annual DR product because customer may easily maintain non-summer load below Firm Service Level (FSL) amount. | 3 | Capacity is annual product based on summer peak period. DR M&V requirement is to maintain load below designated level which is consistent for all products. DR performance is not measured differently in summer vs non-summer

## Package Solutions
PJM Capacity Senior Task Force
Demand Response Issues
Package Solutions
Address short-term Demand Response issues listed in issue charge.
Updated November 12, 2012
ID | Design Component | Importance | Packages
|  |  | Status Quo | Package 1 | Package 2 | Package 3 | Package 4 | Package 5 | Package 6 | Package 7
1
2
3a
3b
3c
5

## Audit Design Components
PJM Capacity Senior Task Force
Demand Response Issues
Design Components - Auditing of DR Contracts
Updated January 22, 2013
ID | Design Component/Issue | Importance | Component Options
|  |  | Status Quo | A | B | C | D | E | F | G
1 | Should PJM have a provision in the tariff for auditing of DR contracts? |  | If DR does not perform they receive a penalty. CSP permitted to aggregated performance across customers. MMU, PJM and FERC OE may investigate on case by case basis as necessary | No; status quo is fair and resonable
2 | Timing/triggers for audits
3 | Entity administering audits
4 | Funding for audits

## Package Solution Timelines (hidden)
Status Quo Timeline
Package 1 Proposed Timeline
Nov
Oct
Sept
Aug
Triennial Review
MRC/MC Vote, waive first read
Dec 1 Deadline: Triennial Review Filing
Oct 31 Deadline: Feedback on report
Sept 1 Deadline: PJM staff publish recommendations
PJM Board Approval
2-weeks required for Board Material Delivery
Nov
Oct
Sept
Aug
Quadrennial Review
Dec 1 Deadline: Triennial Review Filing
Sept 30 Deadline: Feedback on report
July 15 Deadline: PJM staff publish recommendations
PJM Board Approval
2-weeks required for Board Material Delivery
MRC Vote (if first read is waived)
July
MC Vote

## Issue Status
CSTF - 2012 Demand Response Issues
as of 12/2013
# | Item | Owner | Priority | Status/Notes
1 | Auditing of DR Contracts | Langbein | 6 | Education, discussion, and issue identification at 9/20 meeting; from 1/23 meeting, PSEG to provide further detail on component options and bring to the group
2 | DR Resource Testing | Langbein | 2 | Education, discussion, and issue identification at 9/20 meeting
3 | Interaction of Peak Load Contribution ("PLC") with end-user RPM cost assignment and DR Resource RPM revenue, and implication to DR resource auction participation | Langbein | 1 | Education, discussion, and issue identification at 11/9 meeting; Seeking further clarification from MRC on 1/31
4 | Process for DR Resources to change commitment to higher curtailment products in subsequent Delivery-Year auctions | Bastian | Complete | Currently possible, Bastian to provided education at 9/20 meeting
5 | Measurement and Verification of different PJM resources and products | Langbein | 3 | Education, discussion, and issue identification at 11/9 meeting
6 | DR Notification time During Non-Critical Summer Hours | Langbein | Complete | Education & discussion at 11/9 meeting; close this item and reconsider if penalty structures change
7 | Review assumptions used in DR Saturation studies | Planning Committee | Complete | MRC first read, September PC vote, October MRC voted down

## Action Items
12/5/12 meeting action item:
Stakeholders to bring back detailed solution options for the concepts listed below.
# | Concept | Owner
1 | Investigate ways to specify firm vs. interruptible | Dave Mabry
2 | Another measurement of reduction capability (other than PLC) | Katie Guerry
3 | If excess capacity credits at the end of the year; process for awarding the entity the difference. | Bruce Campbell
4 | Investigate differing treatment for proven vs. new DR customers | John Horstmann
5 | Investigate capability to make adjustments and timing | John Horstmann
6 | Develop DR Audit Matrix | CSTF
1/23/13 meeting action items:
# | Concept | Owner
3 | clarfiy issue with MRC on 1/31/13 after diagreement over the interpretation of this issue | PJM, Katie Guerry
1 | Bring design components and specifics to next meeting | Citrolo, Caretta