## May 2023
RPCTF Work Plan | Nov. 8, 2021 | Dec. 3, 2021 | Jan. 7, 2022 | Feb. 7, 2022 | April 4, 2022 | May 9, 2022 | June, 6 2022 | July 8, 2022 | Aug 1, 2022 | Sept. 28, 2022 | Oct 20 2022 | Nov 29, 2022 | Jan. 6, 2023 | Feb 10 2023 | Mar 10 2023 | May 12, 2023 | June 9. 2023 | July 12, 2023 | Aug 9 2023 | Sept/Oct 2023 | Nov 15 2023
Develop/Review Work Plan | X |  | X |  | X | X |  |  |  | X
Education & Joint Fact-Finding | X | X | [7 empty] | X |  |  |  |  | X
Interest Identification | X | X | X
Develop Design Components |  | X | X | X
Document Relative Importance of each Component |  |  | X
Develop Options for each Component |  |  | X | X | X
Narrow Options |  |  |  |  | X
Develop Packages | [5 empty] | X | X |  |  | X
Narrow Packages (Compare Packages to Interests & Importance Ratings) | [7 empty] | X | X | X | X | X | X | X | X | X | X
Consensus Testing | [7 empty] | X |  |  | X | X | X | X | X | X | X
Tier 1/Tier 2 Decision Making | [15 empty] | X | X
Reporting to Parent Committee |  |  | X |  |  |  | X |  | X | [7 empty] | X | MIC | MIC | MRC | MC