## Instructions
Project Proposal Template - version 1
Proposal Template Instructions
General Instructions
Upgrade project requirements: Complete tabs 1, 2, 3, 9 and the appropriate tab 4 or 5 for each project component as identified on tab 3.
Greenfield project requirements: Complete tabs 1, 2, 3, 9 and the appropriate tabs 4 through 7 for each project component as identified on tab 3.
Cost Containment: Proposals submitting a cost containment commitment are required to complete the '10. Cost Contain' tab.
Redaction: PJM's redaction guidelines are posted on pjm.com at the link below. Responses or portions of responses that are deeped proprietary should be included on the 'Redacted Information' tab with a reference back to the response identification number.
http://pjm.com/~/media/planning/rtep-dev/expan-plan-process/ferc-order-1000/rtep-proposal-windows/proposal-redaction-guidelines.ashx
1. | Executive Summary Tab
| 1.a. | Provide the name of the Proposing Entity. If there are multiple entities, please identify each party.
| 1.b. | Provide the RTEP Proposal Window in which this proposal is being submitted.
| 1.c. | Provide the Proposing Entity project proposal id. Use "A, B, C, …", etc. to differentiate between proposals.
| 1.d. | PJM proposal identification
| 1.e. | Provide a general description of the scope of this project (e.g. Project is a new line between X and Y substations utilizing AAA structures. A new bay will be created within the existing substation X footprint. Substation Y will be reconfigured to a breaker and a half with accomodations for the new line.)
| 1.f. | Identify if the proposal or a proposal component span two PJM Transmission Owner zones. I.e. The proposal topology connects equipment owned by more than one Transmission Owner. This group includes transmission that spans two or more affiliated companies (e.g. Meted and Allegheny Power).
| 1.g. | Indicate if the project is being proposed as a solution to a cross-border (e.g. PJM to MISO, PJM to NYISO) issue. (Note: The Proposing Entity is responsible for initiating and satisfying all regional and interregional requirements.)
| 1.h. | Indicate if the Proposing Entity intends to construct, own, operate, and maintain the infrastructure built under this proposal.
| 1.i. | Total current year project cost estimate including estimates for any required Transmission Owner upgrades.
| 1.j. | Total in-service year project cost estimate including estimates for any required Transmission Owner upgrades.
| 1.k. | Project estimated schedule duration in months.
| 1.l. | Indicate if any cost containment commitment is being proposed as part of the project. If yes, the "10. Cost Contain" tab within this project proposal template is to be completed
| 1.m. | If the project provides any known additional benefits above solving the identified violations or constraints, identify those benefits (e.g. reliability, economic, resilience, etc.).
| 1.n. | Confirm that all technical analysis files have been provided for this proposal.
| 1.o. | Confirm that all necessary project diagrams have been provided for this proposal.
| 1.p. | Indicate if company evaluation and operations and maintenance information has been provided for this proposal.
If the answer to the cross-border question above at 1.g. was yes, complete the questions below.
| 1.q.i. | Indicate if an evaluation for interregional cost allocation is desired.
| 1.q.ii. | Indicate if the proposal has been evaluated in a coordinated interregional analysis under the PJM Tariff or Operating Agreement provisions. Specify the analysis and applicable Tariff or Operating Agreement provisions.
| 1.q.iii. | List the specific regional and interregional violations and issues from the regional and/or interregional analyses that identified the violations and issues addressed by the proposal.
2. | Overloaded Facilities Tab
| 2.a. | Identify the criteria violation(s) or system constraint(s) that the proposed project solves or mitigates.
| 2.b. | Identify the criteria violation(s) or system constraint(s) that the proposed project causes or does not address.
| 2.c. | Identify the Market Efficiency flowgate(s) the proposed project mitigates.
3. | Major Project Components Tab
| 3.a. | Provide a description for each major project component. Each project component will require the completion of the tab corresponding to the category of the component ("Greenfield Substation Component" tab for any proposed new substation, for example).
| 3.b. | Provide a component project cost breakdown into the identified categories along with a total component cost. Costs should be in current year dollars.
| 3.c. | If this proposal is being submitted as Market Efficiency project, provide an in-service year component project total cost.
| 3.d. | Identify the entity who will be designated the component.
4. | Transmission Line Reconductor/Rebuild Component Tab
| 4.a. | Provide the corresponding component number from the "Project Components" tab of the proposal template.
| 4.b. | Identify the line terminal points. Add additional spaces if required.
Existing line physical characteristics
| 4.c. | Provide the size and type conductor that will be removed.
| 4.d. | Indicate whether the existing line hardware will be reused. If so, provide the age and condition of the hardware.
| 4.e. | Provide the condition and age of the existing structures. Describe the findings of any recent inspections or of analysis that has indicated a need for structural repair or reinforcement to re-conductor the line.
| 4.f. | Describe the terrain that the existing line traverses. Additionally, provide a Google Earth .KMZ file with the existing line path as an included document with the project proposal package.
Reconductor/rebuild component plan
| 4.g. | Provide the target ratings for the line.
| 4.h. | Provide the type and size of the conductor to be installed.
| 4.i. | If the shield wire is to be replaced, identify the type and size to be used.
| 4.j. | Describe the amount of the line that is anticipated to be rebuilt versus reconductored. Provide any assumptions that were used in arriving at this determination. If specific line sections have been identified for rebuild, provide route maps for (or specify in a Google Earth .KMZ file) those segments and identify the areas.
| 4.k. | Describe the segments of the existing right-of-way that will need to be expanded or any newly required rights-of-way that will be required. If new or expanded right-of-way is required, provide route maps for (or specify in a Google Earth .KMZ file) those segments and identify the areas.
| 4.l. | Describe any files or information that has been redacted from this section and provide the basis for the redaction.
5. | Substation Upgrade Component Tab
| 5.a. | Provide the corresponding component number from the "Project Components" tab of the proposal template.
| 5.b. | Identify the name of the existing substation where the upgrade will take place.
| 5.c. | Describe the scope of the upgrade work at the identified substation.
| 5.d. | Describe any new substation equipment and provide the equipment ratings.
| 5.e. | Describe the assumptions that were made about the substation that were used in developing the scope and cost for the upgrade. For example, the use of a bay that appears to be available, the proposed use of an open area within the substation or the relocation of existing equipment.
| 5.f. | If the upgrade changes or expands upon the substation configuration provide a single line diagram and a station general arrangement drawing. These documents should be provided on the 'Redacted Information' tab under the appropriate project component.
| 5.g. | If the substation fence needs to be expanded, indicate the real-estate plan for acquiring the needed land. Also, provide a Google Earth .KMZ file detailing the expansion.
| 5.h. | Describe any files or information that has been redacted from this section and provide the basis for the redaction.
6. | Transmission Line Component Tab
| 6.a. | Provide the corresponding component number from the "Project Components" tab of the proposal template.
| 6.b. | Provide the substation endpoints for the proposed transmission line component.
| 6.c. | Provide the target ratings for the proposed line.
| 6.d. | Provide the proposed conductor type and size.
| 6.e. | Provide a general description of the line, including nominal voltage, whether the facility will be AC or DC and if the construction will be overhead, underground, submarine or some combination.
| 6.f. | Provide a general description of the evaluated routes or routing study area. Provide a Google Earth .KMZ file with the evaluated routes or study plan.
| 6.g. | Describe the terrain traversed by the proposed new line.
| 6.h. | Route description by segment that includes lengths and widths and classified by whether the segment will be new right of way, an expansion of an existing right of way or use an existing right of way. This information may be included with the Google Earth .KMZ.
| 6.i. | Provide the project right of way and land acquisition plan and approach for both public and private lands.
| 6.j. | Provide the location and plan for any transmission facility crossings.
| 6.k. | Provide an assessment of the potential environmental impacts (i.e. environmental impact study requirements, environmental permitting, sediment, and erosion control issues).
| 6.l. | Proposed tower characteristics such as monopole, lattice, wood h-frame design, double or single circuit, and horizontal, vertical or delta conductor configurations. Note, preliminary drawings for proposed structure types are acceptable in place of a written description.
| 6.m. | Describe any files or information that has been redacted from this section and provide the basis for the redaction.
7. | Greenfield Substation Component Tab
| 7.a. | Provide the corresponding component number from the "Project Components" tab of the proposal template.
| 7.b. | Provide the name for the proposed substation.
| 7.c. | Provide the latitude and longitude (in decimal degrees) of the site(s) evaluated for the substation.
| 7.d. | Provide a general description of the substation. Also, provide a single line diagram and general arrangement drawing.
| 7.e. | Describe the major substation equipment and provide the equipment ratings.
| 7.f. | Describe the required site size, geography and current land use for the proposed site(s).
| 7.g. | Provide an assessment of the potential environmental impacts (i.e. environmental impact study requirements, environmental permitting, sediment, and erosion control issues).
| 7.h. | Community and landowner outreach plan
| 7.i. | Provide the project land acquisition plan and approach for both public and private lands.
| 7.j. | Describe any files or information that has been redacted from this section and provide the basis for the redaction.
8. | Redacted information Tab
Provide all redacted information on this tab with a reference to the tab and specific question identification.
9. | Project Financial Information Tab
Project Schedule
| 9.a. | Provide the planned construction period, include the month and year of when capital spend will begin, when construction will begin and when construction will end. The final construction month should be the month preceding the commercial operation month.
Project Capital Expenditures
| 9.b. | Provide, in present year dollars, capital expenditure estimates by year for the Proposing Entity, work to be completed by others (e.g. incumbent TO) and total project. Capital expenditure estimates should include all capital expenditure, including any ongoing expenditures, for which the Proposing Entity plans to seek FERC approval for recovery.
| 9.c. | Even if AFUDC is not going to be employed, provide a yearly AFUDC cash flow.
| 9.d. | Provide any assumptions for the capital expenditure estimate (e.g. design assumptions, weather, manpower needed and work schedule, number of hours per day, construction area access, etc.).
| 9.e. | Describe any files or information that has been redacted from this section and provide the basis for the redaction.
10. | Cost Containment Commitment Tab
| 10.a. | Provide a description of the cost containment mechanism being proposed.
| 10.b. | Indicate what project scope is covered by the proposed cost containment commitment. Identify the components covered by number.
| 10.b.i. | Provide, in present year dollars and year of occurrence dollars, the Proposing Entity's proposed binding cap on capital expenditures.
| 10.b.ii. | Provide any additional information related to the cap on capital expenditures, including but not limited to: if AFUDC is included in the cap, if all costs prior to commercial operation date are included in the cap, if the cap includes a variable or fixed inflation rate, etc.
| 10.b.iii. | Indicate which components of capital costs fall under the cost cap.
| 10.c. | Describe any other cost containment measures not detailed above.
| 10.d. | Provide language to be included in the Designated Entity Agreement that expresses the legally binding commitment of the developer to the construction cost cap.
| 10.e. | Explain any plans the proposing entity has in place to address the situation where project actual costs exceed the proposed cost containment commitment.
| 10.f. | Describe any files or information that has been redacted from this section and provide the basis for the redaction.

## 1. Executive Summary
Executive Summary
To be publically posted by PJM
Blue indicates input cells for the Proposing Entity to complete
Orange indicates input cells for PJM to complete
1. | Executive Summary
|  | Instructions |  | Inputs
|  | Provide the name of the Proposing Entity. If there are multiple entities, please identify each party. | 1.a. | Proposing Entity name | Dominion Energy Virginia
|  | Provide the RTEP Proposal Window in which this proposal is being submitted. | 1.b. | Proposal window | 2018 RTEP Proposal Window 1
|  | Provide the Proposing Entity project proposal id. Use "A, B, C, …", etc. to differentiate between proposals. | 1.c. | Proposal identification | E
|  | PJM proposal identification | 1.d. | PJM proposal identification
|  | Provide a general description of the scope of this project (e.g. Project is a new line between X and Y substations utilizing AAA structures. A new bay will be created within the existing substation X footprint. Substation Y will be reconfigured to a breaker and a half with accomodations for the new line.) | 1.e. | General project description
Install a 50 MVAR fixed shunt reactor at Pentagon Substation on the 69kV bus
|  | Identify if the proposal or a proposal component span two PJM Transmission Owner zones. I.e. The proposal topology connects equipment owned by more than one Transmission Owner. This group includes transmission that spans two or more affiliated companies (e.g. Meted and Allegheny Power). | 1.f. | Tie line impact | No
|  | Indicate if the project is being proposed as a solution to a cross-border (e.g. PJM to MISO, PJM to NYISO) issue. (Note: The Proposing Entity is responsible for initiating and satisfying all regional and interregional requirements.) | 1.g. | Interregional project | No
|  | Indicate if the Proposing Entity intends to construct, own, operate, and maintain the infrastructure built under this proposal. | 1.h. | Construct, own, operate and maintain | Yes
|  | Total current year project cost estimate including estimates for any required Transmission Owner upgrades. | 1.i. | Project cost estimate (current year) | 3160562
|  | Total in-service year project cost estimate including estimates for any required Transmission Owner upgrades. | 1.j. | Project cost estimate (in-service year) | 3873539
|  | Project estimated schedule duration in months. | 1.k. | Project schedule duration | 32
|  | Indicate if any cost containment commitment is being proposed as part of the project. If yes, the "10. Cost Contain" tab within this project proposal template is to be completed | 1.l. | Cost containment commitment | No
|  | If the project provides any known additional benefits above solving the identified violations or constraints, identify those benefits (e.g. reliability, economic, resilience, etc.). | 1.m. | Additional benefits
All work will be contained within the existing Pentagon substation.
|  | Confirm that all technical analysis files have been provided for this proposal. | 1.n. | Technical analysis files provided
|  | Confirm that all necessary project diagrams have been provided for this proposal. | 1.o. | Project diagram files provided
|  | Indicate if company evaluation and operations and maintenance information has been provided for this proposal. | 1.p. | Company evaluation and operations and maintenance information provided
If the answer to the cross-border question above at 1.g. was yes, complete the questions below.
|  | Indicate if an evaluation for interregional cost allocation is desired. | 1.q.i. | Interregional Cost Allocation Evaluation | No
|  | Indicate if the proposal has been evaluated in a coordinated interregional analysis under the PJM Tariff or Operating Agreement provisions. Specify the analysis and applicable Tariff or Operating Agreement provisions. | 1.q.ii. | Evaluated in interregional analysis under PJM Tariff or Operating Agreement provisions | No
If 'yes,' specify analysis and applicable Tariff or Operating Agreement provisions
|  | List the specific regional and interregional violations and issues from the regional and/or interregional analyses that identified the violations and issues addressed by the proposal. | 1.q.iii. | Regional and Interregional violations and issues from the Regional and/or Interregional analyses that identified the violations and issues addressed by the proposal.

## 2. Overloaded Facilities
Overloaded Facilities
To be publically posted by PJM
Blue indicates input cells for the Proposing Entity to complete
2. | Overloaded Facilities
|  | Facilities addressed by the proposed project | [9 empty] | Facilities not addressed/caused by the proposed project | [9 empty] | Market Efficiency flowgate(s) addressed by the proposed project
|  | Instructions: | Identify the criteria violation(s) or system constraint(s) that the proposed project solves or mitigates. | [8 empty] | Instructions: | Identify the criteria violation(s) or system constraint(s) that the proposed project causes or does not address. | [8 empty] | Instructions: | Identify the Market Efficiency flowgate(s) the proposed project mitigates.
| 2.a. | FG # | Analysis Type | From Bus # | Facility Name | To Bus # | To Bus Name | CKT | Voltage | Area | 2.b. | Unique Proposer Generated ID | Analysis Type | Bus # | Facility Name | To Bus # | To Bus Name | CKT | Voltage | Area | 2.c. | FG# | Facility Name | Area | Type | Frequency (Hours) | Market Congestion ($ millions) | Frequency (Hours) | Market Congestion ($ millions)
|  | N1-SVH1 | Summer N-1 High Voltage | 314185 | 6RADNOR |  |  |  | 230kV | 345
|  | N1-SVH2 | Summer N-1 High Voltage | 314071 | 6PENTAGN |  |  |  | 230kV | 345

## 3. Project Components
Major Project Components
To be publically posted by PJM
Blue indicates input cells for the Proposing Entity to complete
3. | Major Project Components
Instructions
|  |  |  | Component 1 | Component 2 | Component 3 | Component 4 | Component 5 | Component 6 | Component 7 | Component 8 | Component 9 | Component 10
| Provide a description for each major project component. Each project component will require the completion of the tab corresponding to the category of the component ("Greenfield Substation Component" tab for any proposed new substation, for example). | 3.a. | Component description(s) | Install a 50 MVAR fixed shunt reactor and a 69kV breaker at Pentagon Substation on the 69kV bus
|  | 3.b. | Component cost (current year)
| Provide a component project cost breakdown into the identified categories along with a total component cost. Costs should be in current year dollars. |  | Engineering and design
Permitting / routing / siting
ROW / land acquisition
Materials and equipment
Construction and commissioning
Construction management
Overheads and miscellaneous costs
Contingency
|  |  | Total component cost |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| If this proposal is being submitted as Market Efficiency project, provide an in-service year component project total cost. | 3.c. | Component cost (in-service year)
| Identify the entity who will be designated the component. | 3.d. | Construction responsibility | Dominion Energy

## 4. Reconduct-Rebuild Comp
Reconductor/Rebuild Transmission Line Component
To be publically posted by PJM
Blue indicates input cells for the Proposing Entity to complete
4. | Transmission Line Reconductor/Rebuild Component
|  | Instructions |  | Inputs - 1 | Inputs - 2 | Inputs - 3 | Inputs - 4
|  | Provide the corresponding component number from the "Project Components" tab of the proposal template. | 4.a. | Component number | Component number | Component number | Component number
|  | Identify the line terminal points. Add additional spaces if required. | 4.b. | Terminal points | Terminal points | Terminal points | Terminal points
|  |  |  | Existing Line Physical Characteristics | Existing Line Physical Characteristics | Existing Line Physical Characteristics | Existing Line Physical Characteristics
|  | Provide the size and type conductor that will be removed. | 4.c. | Existing conductor size and type | Existing conductor size and type | Existing conductor size and type | Existing conductor size and type
|  |  | 4.d. | Existing hardware plan | Existing hardware plan | Existing hardware plan | Existing hardware plan
Indicate whether the existing line hardware will be reused. If so, provide the age and condition of the hardware.
|  |  | 4.e. | Existing tower line characteristics | Existing tower line characteristics | Existing tower line characteristics | Existing tower line characteristics
Provide the condition and age of the existing structures. Describe the findings of any recent inspections or of analysis that has indicated a need for structural repair or reinforcement to re-conductor the line.
|  |  | 4.f. | Terrain description | Terrain description | Terrain description | Terrain description
Describe the terrain that the existing line traverses. Additionally, provide a Google Earth .KMZ file with the existing line path as an included document with the project proposal package.
|  |  |  | Reconductor/Rebuild Component Plan | Reconductor/Rebuild Component Plan | Reconductor/Rebuild Component Plan | Reconductor/Rebuild Component Plan
|  | Provide the target ratings for the line. | 4.g. | Component target ratings | Component target ratings | Component target ratings | Component target ratings
|  | Provide the type and size of the conductor to be installed. | 4.h. | Proposed conductor size and type | Proposed conductor size and type | Proposed conductor size and type | Proposed conductor size and type
|  | If the shield wire is to be replaced, identify the type and size to be used. | 4.i. | Proposed shield wire size and type | Proposed shield wire size and type | Proposed shield wire size and type | Proposed shield wire size and type
|  |  | 4.j. | Rebuild portion | Rebuild portion | Rebuild portion | Rebuild portion
Describe the amount of the line that is anticipated to be rebuilt versus reconductored. Provide any assumptions that were used in arriving at this determination. If specific line sections have been identified for rebuild, provide route maps for (or specify in a Google Earth .KMZ file) those segments and identify the areas.
|  |  | 4.k. | Right of way | Right of way | Right of way | Right of way
Describe the segments of the existing right-of-way that will need to be expanded or any newly required rights-of-way that will be required. If new or expanded right-of-way is required, provide route maps for (or specify in a Google Earth .KMZ file) those segments and identify the areas.
|  |  | 4.l. | Redacted information | Redacted information | Redacted information | Redacted information
Describe any files or information that has been redacted from this section and provide the basis for the redaction.

## 5. Sub Upgrade Comp
Substation Upgrade Component
To be publically posted by PJM
Blue indicates input cells for the Proposing Entity to complete
5. | Substation Upgrade Component
|  | Instructions |  | Inputs-1 |  | Inputs-1 | Inputs-3 | Inputs-4
|  | Provide the corresponding component number from the "Project Components" tab of the proposal template. | 5.a. | Component number | 1 | Component number | Component number | Component number
|  | Identify the name of the existing substation where the upgrade will take place. | 5.b. | Substation | Pentagon | Substation | Substation | Substation
|  |  | 5.c. | Substation upgrade scope |  | Substation upgrade scope | Substation upgrade scope | Substation upgrade scope
|  | Describe the scope of the upgrade work at the identified substation. |  | Install a 50 MVAR fixed shunt reactor and a 69kV breaker at Pentagon Substation on the 69kV bus
|  |  | 5.d. | New equipment description |  | New equipment description | New equipment description | New equipment description
|  | Describe any new substation equipment and provide the equipment ratings. |  | One (1) 69kV breaker - rated 2000A One (1) fixed shunt reactor - rated 50 MVAR
|  |  | 5.e. | Substation assumptions |  | Substation assumptions | Substation assumptions | Substation assumptions
|  | Describe the assumptions that were made about the substation that were used in developing the scope and cost for the upgrade. For example, the use of a bay that appears to be available, the proposed use of an open area within the substation or the relocation of existing equipment. |  | The new reactor bank and new 69kV breaker will be placed in the vacant transformer bay. The existing 230kV circuit switcher and the existing 69kV breaker (for spare transformer) will be removed.
|  | If the upgrade changes or expands upon the substation configuration provide a single line diagram and a station general arrangement drawing. These documents should be provided on the 'Redacted Information' tab under the appropriate project component. | 5.f. | Substation drawings |  | Substation drawings | Substation drawings | Substation drawings
|  |  | 5.g. | Real-estate plan |  | Real-estate plan | Real-estate plan | Real-estate plan
|  | If the substation fence needs to be expanded, indicate the real-estate plan for acquiring the needed land. Also, provide a Google Earth .KMZ file detailing the expansion. |  | All work will be completed inside the existing substation fence.
|  |  | 5.h. | Redacted information |  | Redacted information | Redacted information | Redacted information
|  | Describe any files or information that has been redacted from this section and provide the basis for the redaction. |  | 5f

## 6. Greenfield Line Comp
Greenfield Transmission Line Component
To be publically posted by PJM
Blue indicates input cells for the Proposing Entity to complete
6. | Transmission Line Component
|  | Instructions |  | Inputs - 1 | Inputs - 2 | Inputs - 3 | Inputs - 4
|  | Provide the corresponding component number from the "Project Components" tab of the proposal template. | 6.a. | Component Number | Component Number | Component Number | Component Number
|  | Provide the substation endpoints for the proposed transmission line component. | 6.b. | Line terminal points | Line terminal points | Line terminal points | Line terminal points
|  | Provide the target ratings for the proposed line. | 6.c. | Project ratings | Project ratings | Project ratings | Project ratings
|  | Provide the proposed conductor type and size. | 6.d. | Conductor type and size | Conductor type and size | Conductor type and size | Conductor type and size
|  |  | 6.e. | General line description | General line description | General line description | General line description
Provide a general description of the line, including nominal voltage, whether the facility will be AC or DC and if the construction will be overhead, underground, submarine or some combination.
|  |  | 6.f. | General route description | General route description | General route description | General route description
Provide a general description of the evaluated routes or routing study area. Provide a Google Earth .KMZ file with the evaluated routes or study plan.
|  |  | 6.g. | Terrain description | Terrain description | Terrain description | Terrain description
Describe the terrain traversed by the proposed new line.
|  |  | 6.h. | Right of way plan by segment | Right of way plan by segment | Right of way plan by segment | Right of way plan by segment
Route description by segment that includes lengths and widths and classified by whether the segment will be new right of way, an expansion of an existing right of way or use an existing right of way. This information may be included with the Google Earth .KMZ.
|  |  | 6.i. | ROW and land acquisition plan | ROW and land acquisition plan | ROW and land acquisition plan | ROW and land acquisition plan
Provide the project right of way and land acquisition plan and approach for both public and private lands.
|  |  | 6.j. | Transmission facility crossings | Transmission facility crossings | Transmission facility crossings | Transmission facility crossings
Provide the location and plan for any transmission facility crossings.
|  |  | 6.k. | Environmental impacts | Environmental impacts | Environmental impacts | Environmental impacts
Provide an assessment of the potential environmental impacts (i.e. environmental impact study requirements, environmental permitting, sediment, and erosion control issues).
|  |  | 6.l. | Tower characteristics | Tower characteristics | Tower characteristics | Tower characteristics
Proposed tower characteristics such as monopole, lattice, wood h-frame design, double or single circuit, and horizontal, vertical or delta conductor configurations. Note, preliminary drawings for proposed structure types are acceptable in place of a written description.
|  |  | 6.m. | Redacted information | Redacted information | Redacted information | Redacted information
Describe any files or information that has been redacted from this section and provide the basis for the redaction.

## 7. Greenfield Sub Comp
Greenfield Substation Component
To be publically posted by PJM
Blue indicates input cells for the Proposing Entity to complete
7. | Greenfield Substation Component
|  | Instructions |  | Inputs - 1 | Inputs - 2 | Inputs - 3 | Inputs - 4
|  | Provide the corresponding component number from the "Project Components" tab of the proposal template. | 7.a. | Component number | Component number | Component number | Component number
|  | Provide the name for the proposed substation. | 7.b. | Proposed substation name | Proposed substation name | Proposed substation name | Proposed substation name
|  | Provide the latitude and longitude (in decimal degrees) of the site(s) evaluated for the substation. | 7.c. | Evaluated location(s) | Evaluated location(s) | Evaluated location(s) | Evaluated location(s)
|  |  | 7.d. | Substation description | Substation description | Substation description | Substation description
Provide a general description of the substation. Also, provide a single line diagram and general arrangement drawing.
|  |  | 7.e. | Substation equipment | Substation description | Substation description | Substation description
Describe the major substation equipment and provide the equipment ratings.
|  |  | 7.f. | Geography and land use | Geography and land use | Geography and land use | Geography and land use
Describe the required site size, geography and current land use for the proposed site(s).
|  |  | 7.g. | Environmental assessment | Environmental assessment | Environmental assessment | Environmental assessment
Provide an assessment of the potential environmental impacts (i.e. environmental impact study requirements, environmental permitting, sediment, and erosion control issues).
|  |  | 7.h. | Outreach plan | Outreach plan | Outreach plan | Outreach plan
Community and landowner outreach plan
|  |  | 7.i. | Land acquisition plan | Land acquisition plan | Land acquisition plan | Land acquisition plan
Provide the project land acquisition plan and approach for both public and private lands.
|  |  | 7.j. | Redacted information | Redacted information | Redacted information | Redacted information
Describe any files or information that has been redacted from this section and provide the basis for the redaction.

## 8. Redacted Information
Redacted Information
8. | Redacted information
Redacted financial information
| Question ID | Redacted response
| 3b | Proprietary Information
Cost containment redacted information
| Question ID | Redacted response
| 5f | CEII protected information
Component 1 redacted information
| Question ID | Redacted response
| 9b,c,d | Proprietary Information
Component 2 redacted information
| Question ID | Redacted response
Component 3 redacted information
| Question ID | Redacted response
Component 4 redacted information
| Question ID | Redacted response
Component 5 redacted information
| Question ID | Redacted response
Component 6 redacted information
| Question ID | Redacted response
Component 7 redacted information
| Question ID | Redacted response
Component 8 redacted information
| Question ID | Redacted response
Component 9 redacted information
| Question ID | Redacted response
Component 10 redacted information
| Question ID | Redacted response

## 9. Financial
Project Financial Information
To be publically posted by PJM
Blue indicates input cells for the Proposing Entity to complete
9. | Project Financial Information
|  | Instructions |  | Inputs
Project Schedule
|  | Provide the planned construction period, include the month and year of when capital spend will begin, when construction will begin and when construction will end. The final construction month should be the month preceding the commercial operation month. | 9.a. | Capital spend start date (Mo-Yr) | 2020-10-01
|  |  |  | Construction start date (Mo-Yr) | 2022-10-03
|  |  |  | Commercial operation date (Mo-Yr) | 2023-05-31
Project Capital Expenditures
|  | Provide, in present year dollars, capital expenditure estimates by year for the Proposing Entity, work to be completed by others (e.g. incumbent TO) and total project. Capital expenditure estimates should include all capital expenditure, including any ongoing expenditures, for which the Proposing Entity plans to seek FERC approval for recovery. | 9.b. | Capital expenditure details | Total | 2020-10-01 | 2021-10-01 | 2022-10-03 | 2023-10-05 | 2024-10-06 | 2025-10-08
Engineering and design
Permitting / routing / siting
ROW / land acquisition
Materials and equipment
Construction and commissioning
Construction management
Overheads and miscellaneous costs
Contingency
Proposer total capex
Work by others capex
Total project capex
|  | Even if AFUDC is not going to be employed, provide a yearly AFUDC cash flow. | 9.c. | [7 empty] | 2025-10-08
AFUDC
|  | Provide any assumptions for the capital expenditure estimate (e.g. design assumptions, weather, manpower needed and work schedule, number of hours per day, construction area access, etc.). | 9.d. | Assumptions for the capital expenditure estimate
|  | Describe any files or information that has been redacted from this section and provide the basis for the redaction. | 9.e. | Redacted information
9b,c,d
[11 empty] | Yes | CWIP
[11 empty] | No | AFUDC
Not Yet Determined

## 10. Cost Contain
Cost Containment Commitment
To be publically posted by PJM
Blue indicates input cells for the Proposing Entity to complete
10. | Cost Containment Commitment
|  | Instructions |  | Inputs
|  |  | 10.a. | Cost containment commitment description
Provide a description of the cost containment mechanism being proposed.
|  |  | 10.b. | Project scope covered by the cost containment commitment
Indicate what project scope is covered by the proposed cost containment commitment. Identify the components covered by number.
[6 empty] | No | AFUDC
|  | Provide, in present year dollars and year of occurrence dollars, the Proposing Entity's proposed binding cap on capital expenditures. | 10.b.i. | Cost cap in present year dollars |  |  | Not Yet Determined
Cost cap in in-service year dollars
|  |  | 10.b.ii. | Additional Information on cost cap:
Provide any additional information related to the cap on capital expenditures, including but not limited to: if AFUDC is included in the cap, if all costs prior to commercial operation date are included in the cap, if the cap includes a variable or fixed inflation rate, etc.
|  |  | 10.b.iii. | Cost containment capital expenditure exemptions
|  | Indicate which components of capital costs fall under the cost cap. |  | Capital cost component | Component covered by cost containment
|  |  |  | Engineering and design | Choose Yes or No
|  |  |  | Permitting / routing / siting | Choose Yes or No
|  |  |  | ROW / land acquisition | Choose Yes or No
|  |  |  | Materials and equipment | Choose Yes or No
|  |  |  | Construction and commissioning | Choose Yes or No
|  |  |  | Construction management | Choose Yes or No
|  |  |  | Overheads and miscellaneous costs | Choose Yes or No
|  |  |  | Taxes | Choose Yes or No
|  |  |  | AFUDC | Choose Yes or No
|  |  |  | Escalation | Choose Yes or No
|  |  | 10.c. | Describe any other Cost Containment Measures not covered above:
Describe any other cost containment measures not detailed above.
|  |  | 10.d. | Cost Commitment Legal Language
Provide language to be included in the Designated Entity Agreement that expresses the legally binding commitment of the developer to the construction cost cap.
|  |  | 10.e. | Actuals Exceed Commitment
Explain any plans the proposing entity has in place to address the situation where project actual costs exceed the proposed cost containment commitment.
|  |  | 10.f. | Redacted information
Describe any files or information that has been redacted from this section and provide the basis for the redaction.
Yes
No